WorldWise Educational Tours

Connecting Learning with Exploration

IMPLEMENTATION  PLAN

1. Strategic Goals

▪ Establish WorldWise as the trusted provider of curriculum-linked educational tours.

▪ Build long-term partnerships with schools, universities, and ministries.

▪ Scale operations gradually: local → regional → international tours.

▪ Ensure financial sustainability through diversified revenue streams.

2. Phased Implementation Roadmap

Phase 1: Foundation & Launch (Months 1–6)

Objectives: Establish brand presence, secure initial clients, pilot local tours.

Key Activities:

▪ Business Setup – Registration, licensing, office setup, staff recruitment.

▪ Program Development – Pilot 5–10 schools per region (Pre-schools, Primary, High Schools and Universities) on local tours and cross-border tours, curriculum integration, safety protocols.

▪ Partnership Building –Ministry of Education and training, Schools, colleges, transport & insurance partners.

▪ Marketing & Branding –  social media, brochures, pilot campaign in 40 schools.

Deliverables: Signed MoU with MoET, First 3–5 tours completed, signed MOUs,+3000 students served.

Phase 2: Regional Expansion (Months 7–18)

Objectives: Expand destinations to neighboring countries, strengthen client base.

Key Activities:

▪ Tour Portfolio Growth – Add South Africa, Mozambique, Botswana tours.

▪ Capacity Building – Hire and train tour guides and educators.

▪ Marketing & Visibility – Education fairs, testimonials, referral programs.

▪ Financial Growth – Corporate sponsorships, educational camps.

Deliverables: 10+ schools annually, 500+ students, 20% revenue growth.

Phase 3: International Tours (Year 2–3)

Objectives: Position WorldWise as an international player, offering global learning.

Key Activities:

▪ International Partnerships – MOUs with schools abroad, embassy collaborations.

▪ Inbound Tourism – Launch 'Study in Eswatini' programs.

▪ Operational Scaling – Regional office in Johannesburg/Pretoria, invest in minibuses.

Deliverables: First international tour, 3 MOUs, 1,000+ learners annually.

Phase 4: Regional Leadership & Sustainability (Year 4 onwards)

Objectives: Become a recognized Southern African leader in educational travel.

Key Activities:

▪ Innovation – Digital learning integration, regional student camps.

▪ Sustainability – Eco-friendly practices, scholarships for underprivileged learners.

▪ Regional Influence – Advisory role to Ministries, hub for educational tourism.

Deliverables: Regional recognition, 2,000+ learners annually, financial sustainability.

3. Key Resources Needed

▪ Human Resources: Educators, tour guides, logistics staff.

▪ Financial Resources: Initial investment ~E20,000 + ongoing revenue & partnerships.

▪ Infrastructure: Office setup, IT systems, transport partnerships.

▪ Partnerships: Schools, universities, ministries, embassies, transport & hospitality providers.

4. Monitoring & Evaluation

▪ Monthly: Track tours conducted, student satisfaction, safety compliance.

▪ Quarterly: Review finances, partnership growth, marketing reach.

▪ Annually: Assess learning outcomes, market share growth, strategic milestones.

5. Implementation Timeline

The following Gantt chart illustrates the phased implementation of WorldWise Educational Tours over 5 years.